- November:

  - Volunteer organizers meet each other; invite Master Gardener Volunteer Coordinator (MGVC), and a member of the board from the Alpine Master Gardener Association (AMGA).

  - Pick days/dates to hold lectures.

- Confirm dates with the AMGA making sure dates & times will not conflict with their meetings.

- Schedule dates with the Otsego County Library.

  - Decide on lecture topics* (ideas in 3-ring binder), and get approval from MGVC and AMGA.

  - Decide who will contact speakers* (Possible speakers in 3-ring binder).

  - Formulate a budget and ask the AMGA Vice President for the money. (Expenses:  Door prizes, thank-you cards & gift certificates-as appropriate, refreshments, napkins & paper plates-as needed).

- November – January

  - Contact speakers, decide specific date speaker will present, coordinate with other volunteers.  Ask for a very short Biography* (example:  5-facts about speaker & topic) which will use in the flyer, on the Public Service Announcement, and to introduce the speaker.

  - Early January send Otsego County Conservation District a list of dates, topics, and speakers so this information may be included in their newsletter.

- February

  - Send speaker confirmation letter* (optional).

- March

  - Make flyer*.  Ask Michigan State University Extension (MSUE) contact to put in the information in the April newsletter. Include in the flyer the dates and speakers and a very short Biography* of the speakers and the lecture topics.

- April

  - Contact (call or write) speakers, remind them of lectures, ask if any special equipment (such as a projector, computer, screen) is needed (do this +/- 2 weeks prior to each lecture thru May).

  - Contact the library and reserve special equipment as needed.

  - At AMGA meeting send around the Treats* sign-up sheet asking for volunteers to bring Drink/Sweet/Salty/Napkins & Paper Plates to lecture for +/- 20 guests.  For any remaining openings, ask the volunteer organizers to sign up.

  - Submit Public Service Announcements (PSA)* to the Gaylord Herald Times (2nd-3rd week of April and thru May) and radio station ((3rd-4th week of April and thru May).

  - Post flyers* (at library-and on Library marquee, Conservation District, places of work, etc.).

- May

  - Contact speakers 1-2 weeks before each lecture.

  - By noon the day before the lecture, call the library and advise how the room needs to be set up (for viewing the screen, or for a demonstration).

  - Half hour before lecture set up room/treats.

  - At the lecture take photos then share photos with the AMGA historian.

  - At lecture pass out survey* and collect after lecture, have people sign in so the door prize may be given.

  - Use the Introduction* form as needed.

  - Send Thank-you notes to the speakers.

  - Update this outline* and other examples in the 3-ring binder as needed

  - Give MGVC the names and information of anyone interested in becoming a Master Gardener or being notified of upcoming events.